Digital Hubs- Implementation Status

| No. | County | Constituency | Ward / Site Name | Model | Implementation Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Murang'a | Kandara | Kiiri Digital Hub (Ithiru ward) | Option 4 | Ongoing at 85% completion rate |
| 2 | Murang'a | Kangema | Kanyenyaini Digital Hub (Kanyenyaini ward) | Option 4 | At 95% completion rate (equipping ongoing) |
| 3 | Murang'a | Kangema | Kangema Digital Hub (Muguru ward) | Option 4 | At 95% completion rate (equipping ongoing) |
| 4 | Nyeri | Nyeri Town | Ruringu Youth Empowerment Centre (Ruringu ward) | Option 4 | Ongoing at 10% (demolition of existing wall to extend building) |
| 5 | Nyeri | Tetu | Tetu Youth Resource Centre (Wamagana ward) | CoE | Ongoing at 1st-floor suspended slab level (hub will be on 1st floor) |
| 6 | Murang'a | Maragua | Makuyu Chiefs Hall Digital Hub (Makuyu ward) | Basic | Ongoing at 1st-floor suspended slab; NG-CDF to allocate more funds in 2025/26 FY |
| 7 | Kiambu | Gatundu South | Kiganjo Digital Hub (Kiganjo ACC’s Office) | Basic | Ongoing at foundation level (5%) |
| 8 | Nyandarua | Ndaragwa | Leshau Pondo Digital Hub - Ndogino (Leshau Pondo ward) | Basic | Ongoing at finishes level (90%) |
| 9 | Murang'a | Mathioya | Kamacharia ICT Hub (Kamacharia ward) | Option 4 | Ongoing at 90% (renovation & installations; operational) |
| 10 | Murang'a | Mathioya | Gitugi ICT Hub (Gitugi ward) | Option 4 | Ongoing at 90% (renovation & installations; operational) |
| 11 | Murang'a | Mathioya | Kiriaini ICT Hub (Kiru ward) | Option 4 | Ongoing at 90% (renovation & installations; operational) |
| 12 | Kiambu | Kiambu | Ndumberi Youth Empowerment Center (Ndumberi ward) | Option 4 | Ongoing at finishes (90%) |
| 13 | Mandera | Lafey | Lafey Huduma Jitume Digital Centre | CoE | Ongoing at roofing level (gutters being installed); plumbing & wiring ongoing (60%) |
| 14 | Wajir | Eldas | Elnur/Tulatula Digital Hub | Standard | Ongoing at finishes level; roofing done (60%) |
| 15 | Mombasa | Jomvu | Jomvu Kuu Digital Hub (Jomvu ward) | Basic | Ongoing at 3% (site handed over 22 Aug 2025; contractor mobilizing) |
| 16 | Kwale | Msambweni | Msambweni Youth & Opportunity Centre ICT Hub (Ukunda ward) | Option 4 | Ongoing (procurement of workstations underway; building existing) |
| 17 | Kwale | Matuga | Kubo South Digital Hub (Lukore Chiefs Office compound) | Basic | Ongoing at finishing level (80%) |
| 18 | Kwale | Matuga | Mkongani Digital Hub (Mkongani ward) | Basic | Ongoing at finishing level; windows & doors fitting (80%) |
| 19 | Kwale | Matuga | Waa / Ngombeni Digital Hub (Kombani Chief Office compound) | Basic | Ongoing at finishing level (65%) |
| 20 | Kwale | Kinango | Samburu / Chengoni Huduma Jitume Digital Centre (Samburu Chengoni ward) | CoE | Construction ongoing; roofing stage (60%) |
| 21 | Kilifi | Rabai | Huduma Jitume Digital Centre – Rabai (Rabai-Kisurutini ward) | CoE | Construction ongoing; ring-beam stage (30%) |
| 22 | Kilifi | Malindi | Huduma Centre Malindi (Shella ward) | Basic | Site handed over; foundation stage (5%) |
| 23 | West Pokot | Kapenguria | Constituency Digital Hubs at Kitalekapel TTI (Riwo ward) | Standard | Ongoing at roofing level (40%) |
| 24 | Baringo | Tiaty | Chemolingot Town ICT Hub | Standard | Ongoing (site handed over recently) |
| 25 | Uasin Gishu | Soy | Ziwa Sirikwa Chief's Office | Standard | Ongoing at finishes level (95%) |
| 26 | Uasin Gishu | Soy | Mois Bridge Chief’s Office | Standard | Ongoing at finishes level (95%) |
| 27 | Uasin Gishu | Soy | Chuiyat Sub Location ICT Hub | Basic | Ongoing at foundation stage (10%) |
| 28 |  | Sigor | Lomut Digital Hub | Standard | Ongoing at foundation level (10%) |
| 29 | Busia | Funyula | Samia Resource Jitume Centre (Nangina ward) | Center of excellence | Ongoing; walling on ground floor (15%) |
| 30 | Busia | Teso South | Huduma Jitume Digital Centre - Aterait (Chakol ward) | Center of excellence | Contractor on site; plastering 70% |
| 31 | Busia |  | Simba Chai Chief’s Office Digital Hub | Basic | Ongoing; contractor on site; allocate funds in 2025/26 FY |
| 32 | Busia | Sitikho | Sitikho Ward ICT Hub (Kuywa Dispensary) | Basic | Ongoing; walling level (20%) |
| 33 | Busia | Misikhu | Misikhu Ward Digital Hub (Sirende Chief's Office) | Basic | Ongoing; slabbing (10%) |
| 34 | Bungoma | Sirisia | Sirisia Digital HUB - Lwandanyi | Standard | Ongoing; roofing level (70%) |
| 35 | Bungoma | Kabuchai | Kabuchai Constituency Digital Hubs - Chwele | Basic | Ongoing; lintel level (30%) |
| 36 | Kakamega | Likuyani | Huduma Jitume Digital Centre (Kongoni ward) | CoE | Ongoing; roof slab finishes (54%) |
| 37 | Kakamega | Likuyani | Mabusi Digital Hub (Sinoko ward) | Basic | Ongoing; internal plastering (60%) |
| 38 | Kakamega | Lurambi | Lurambi NG-CDF Office Digital Hub (Sheywe) | Standard | Ongoing; plastering works |
| 39 | Isiolo | Isiolo South | Isiolo South NG-CDF ICT Centre | Basic | Ongoing; 98% (pending installation of furniture) |
| 40 | Marsabit | Moyale | Digital Hub at Moyale NG-CDF Office Compound | Basic | Ongoing; 98% (pending installation of furniture) |
| 41 | Marsabit | North Horr | Digital Hub at Maikona Ward | Basic | Ongoing; 98% (pending installation of furniture) |
| 42 | Marsabit | North Horr | North Horr Ward Digital Hub | Standard | Ongoing; 98% (pending installation of furniture) |
| 43 | Meru | South Imenti | Kathera Innovation Communication Technology Centre | Option 4 (Conversion) | Ongoing; 95% (pending painting & furniture) |
| 44 | Meru | Abogeta West | Abogeta West ICT Centre | Option 4 (Conversion) | Ongoing; 66% (pending fencing, gate, ramp, painting & furniture) |
| 45 | Meru | Igoji | Deputy County Commissioner Dept Offices (Igoji) | Option 4 (Conversion) | Ongoing; 94% (pending furniture) |
| 46 | Meru | Igembe South | Constituency Innovation Hub (Antubochiu Chiefs ground) | Standard | Ongoing; 37% (substructure & walling) |
| 47 | Meru | Igembe South | Constituency Innovation Hub (Maua Chiefs camp ground) | Standard | Ongoing; 37% (substructure & walling) |
| 48 | Meru | Igembe South | Constituency Innovation Hub (Mutio Kiama ACC Office ground) | Standard | Ongoing; 37% (substructure & walling) |
| 49 | Meru | Igembe Central | Igembe East Ward Digital Hub | Standard | Ongoing; 35% |
| 50 | Meru | Igembe Central | Akirang'ondu Ward Digital Hub | Standard | Ongoing; 35% |
| 51 | Meru | Tigania West | Kianjai Chief’s Office Digital Hub (Kianjai ward) | Basic | Ongoing; 70% |
| 52 | Meru | Tigania East | Mikinduri Ward ICT Hub | Standard | Ongoing; 45% |
| 53 | Meru | Tigania East | Thangatha Ward ICT Hub | Standard | Ongoing; 45% |
| 54 | Meru | Buuri | Ontulili Digital Hub | Basic | Ongoing; 98% (pending furniture) |
| 55 | Meru | Buuri | Kiirua Digital Hub | Standard | Ongoing; 98% (pending furniture) |
| 56 | Meru | Buuri | Kibirichia Digital Hub | Standard | Ongoing; 98% (pending furniture) |
| 57 | Meru | Buuri | Tutua Digital Hub | Standard | Ongoing; 98% (pending furniture) |
| 58 | Meru | Buuri | Timau ICT Hub | Standard | Ongoing; 40% (substructure & walling) |
| 59 | Meru | Buuri | Kisima ICT Hub | Standard | Ongoing; 70% (pending roofing, finishes, electrical & furniture) |
| 60 | Tharaka-Nithi | Tharaka | ICT Hub (Marimanti ward) | Standard | Ongoing; 98% (pending furniture) |
| 61 | Tharaka-Nithi | Maara | Mugumango Digital Hub | Standard | Ongoing; 98% (electrical works ongoing) |
| 62 | Machakos | Kangundo | Kangundo Digital Hub (Kangundo Central ward) | Basic | Ongoing; 98% (pending furniture) |
| 63 | Kitui | Kitui West | Kitui West ICT Hub (Kauwi ward) | Basic | Ongoing; 98% (pending furniture) |
| 64 | Kitui | Kitui West | Matinyani ICT Hub (Matinyani ward) | Basic | Ongoing; 98% (pending furniture) |
| 65 | Machakos | Masinga | Kivaa Chief’s Office with ICT Hub (Kivaa ward) | Standard | Ongoing; 80% (awaiting external & internal finishes, electrical, plumbing, painting & workstations) |
| 66 | Machakos | Yatta | Matuu Digital Hub (Matuu ward) | Standard | Ongoing; 10% (substructure only) |
| 67 | Kitui | Kitui East | Mutitu Digital Hub | Basic | Ongoing; lintel level |
| 68 | Kitui | Kitui East | Chuluni Digital Hub | Basic | Ongoing; foundation level |
| 69 | Kitui | Kitui Central | Ithiani Digital Hub | Basic | Ongoing; roofing stage (40%) |
| 70 | Kitui | Kitui Central | Miambani Digital Hub | Basic | Ongoing; roofing stage (40%) |
| 71 | Siaya | Ugunja | Ugunja Constituency Digital Hub (Ugunja ward) | Basic | Ongoing; plastering complete awaiting painting & tiling (85%) |
| 72 | Siaya | Bondo | Kambajo Digital Hub (West Sakwa ward) | Basic | Ongoing; roofing level (60%) |
| 73 | Homa Bay | Rangwe | Rangwe Constituency Digital Hub (Gem West ward) | Basic | Ongoing; roofing stage |
| 74 | Homa Bay | Suba South | Nyadenda Chief’s Office Digital Hub (Ruma Kaksingri East ward) | Basic | Ongoing; roofing stage (65%) |
| 75 | Homa Bay | Suba South | Kiabuya Chief’s Office Digital Hub (Gwassi South ward) | Basic | Ongoing; gutter beam stage (60%) |
| 76 | Migori | Awendo | Rinya Chief's Camp Digital Hub (South Sakwa ward) | Basic | Ongoing; wall plate level (40%) |
| 77 | Migori | Kuria West | Nyamosense ACC’s Office Digital Hub (Nyamosense/Komosoko ward) | Basic | Ongoing; ring beam level (30%) |
| 78 | Migori | Kuria West | Kehancha Police Station Digital Hub (Bukira East ward) | Basic | Ongoing; roofing level (50%) |
| 79 | Migori | Kuria East | Kegonga Huduma Digital Hub Centre (Ntimaru East ward) | Center of Excellence | Ongoing; foundation level (30%) |
| 80 | Migori | Kuria East | Ntimaru East Digital Hub (Ntimaru East ward) | Standard | Ongoing; foundation slab level (30%) |
| 81 | Kisii | South Mugirango | Nyamarambe Deputy County Commissioner's Office Digital Hub (Bogetenga ward) | Basic | Ongoing; 70% |
| 82 | Nyamira | Kitutu Masaba | Kenyerere Digital Hub (Rigoma ward) | Standard | Ongoing; plastering & fixing doors & windows (80%) |
| 83 | Nyamira | West Mugirango | West Mugirango NG-CDF Office Digital Hub (Township ward) | Option 4 (renovation) | Ongoing; awaiting painting (80%) - connected to NOFBI |
| 84 | Nyamira | North Mugirango | North Mugirango NG-CDF Office Digital Hub (Ekerenyo ward) | Standard | Ongoing; finishes level (requires plastering, painting, flooring) |
| 85 | Laikipia | Laikipia East | Tigithi Jitume ICT Hub (Tigithi ward) | Basic | Ongoing; roofing level |
| 86 | Laikipia | Laikipia North | Ilpolei Jitume ICT Hub (Mukogodo West) | Basic | Ongoing; finishes level (90%) |
| 87 | Laikipia | Laikipia North | Naibor Jitume ICT Hub (Segera ward) | Basic | Ongoing; foundation slab level (20%) |
| 88 | Kericho | Ainamoi | Manyoror ICT Hub (Kapsaos ward) | Basic | Ongoing; ring beam level |
| 89 | Bomet | Bomet East | Merigi Technical Training Institute (Merigi ward) | Basic | Ongoing; finishes level (80%) |
| 90 | Bomet | Bomet East | Chemaner Vocational & Training Centre (Chemaner ward) | Basic | Ongoing; finishes level (80%) |
| 91 | Bomet | Bomet East | Tegat Vocational & Training Centre (Kembu ward) | Basic | Ongoing; finishes level (80%) |
| 92 | Bomet | Bomet East | Kipreres Chief’s Office ICT Hub (Kipreres ward) | Basic | Ongoing; finishes level (80%) |
| 93 | Bomet | Konoin | Mogogosiek Digital Hub (Mogogosiek ward) | Basic | Ongoing; walling stage (20%) |
| 94 | Bomet | Sotik | Rongena Digital Hub (Rongena Manaret ward) | Basic | Ongoing; superstructure walling level (50%) |
| 95 | Bomet | Sotik | Chebilat Digital Hub (Kapletudo ward) | Basic | Ongoing; 50% |
| 96 | Baringo | Eldama Ravine | Kabimoi Chief’s Office ICT HUB (Koibatek ward) | Standard | Ongoing; roofing level |
| 97 | Baringo | Mogotio | Jitume Digital Hubs (Mogotio ward) | Basic | Ongoing; foundation level (10%) |
| 98 | Kajiado | Kajiado North | Olkeri ICT HUB (Olkeri ward) | Basic | Ongoing; installation of workstations & cabling (85%) |
| 99 | Kajiado | Kajiado South | Kimana ICT Hub (Kimana ward) | Option 4 | Ongoing; 90% |
| 100 | Narok | Narok East | Narok East ICT Huduma Jitume Digital Centre (Keekonyokie ward) | Center of Excellence | Ongoing; finishing stage (90%) |
| 101 | Narok | Narok West | Mulot Chief’s Office ICT Hub | Basic | Ongoing; foundation level |
| 102 | Narok | Narok West | Ngosuani Deputy County Commissioner’s Office ICT Hub | Basic | Ongoing; foundation level |
| 103 | Narok | Narok South | Melelo Digital Hub | Basic | Ongoing; lintel level (70%) |
| 104 | Nakuru | Njoro | Njoro ICT HUB (Njoro ward) | Basic model | Ongoing; roofing level (40%) |
| 105 | Nakuru | Bahati | Kiamaina Digital Hub | Option 4 | Ongoing; 10% (partitioning) |
| 106 | Nakuru | Bahati | Bahati Digital Hub | Option 4 | Ongoing; 60% (installation of workstations) |
| 107 | Nakuru | Molo | Elburgon Digital Hub (Elburgon ward) | Basic | Ongoing; 60% |
| 108 | Nairobi | Mathare | Ngei | CoE | Ongoing; 50% |

CENTRAL REGION

| No. | Region | County | Constituency | Ward / Location | Model | Status / Completion |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Central | Kirinyaga | Gichugu | Gatugura – Kabare Ward | Standard | Complete |
| 2 | Central | Kirinyaga | Gichugu | Karumande – Karumandi Ward | Standard | Complete |
| 3 | Central | Kirinyaga | Gichugu | Gichugu West ACC – Kabare Ward | Standard | Complete |
| 4 | Central | Kirinyaga | Gichugu | Gichugu TVC – Ngariama Ward | Option 4 | Complete |
| 5 | Central | Murang’a | Kangema | Kanyenyaini – Kanyenyaini Ward | Option 4 | 95% (equipping ongoing) |
| 6 | Central | Murang’a | Kangema | Kangema Digital Hub – Muguru Ward | Option 4 | 95% completion |
| 7 | Central | Nyandarua | Kipipiri | Kimende Digital Hub | Option 4 | Complete (awaiting furniture) |
| 8 | Central | Kirinyaga | Mwea | Tebere CoE | CoE | Construction complete, awaiting furniture |
| 9 | Central | Kirinyaga | Ndia | Kirinyaga West DCC’s Office – Mukure Ward | Basic | Complete, awaiting computers |
| 10 | Central | Kirinyaga | Ndia | Upper Sagana Primary School – Kariti Ward | Basic | Complete, awaiting internet & computers |
| 11 | Central | Nyandarua | Oljoro Orok | Charagita Digital Hub – Charagita Ward | Standard | 90% complete, painting works pending |
| 12 | Central | Nyandarua | Oljoro Orok | WERU CIH Hub | – | Operational (old CIH, no staff) |
| 13 | Central | Nyandarua | Oljoro Orok | Gathanji CIH Hub | – | Operational (old CIH, no staff) |
| 14 | Central | Kiambu | Ruiru | Ruiru Chief's Office | Basic | Complete & operational |
| 15 | Central | Kiambu | Ruiru | Ruiru Technical & Vocational Training Institute | Option 4 | Complete & operational |
| 16 | Central | Nyeri | Tetu | Muhoya Chief's Camp Hub – Dedan Kimathi Ward | Option 4 | Complete & operational (funds allocated) |
| 17 | Central | Nyeri | Tetu | Karundu Chief's Camp Hub – Wamagana Ward | Option 4 | Complete & operational (funds allocated) |
| 18 | Central | Kiambu | Githunguri | Githunguri Digital Hub – Githunguri Ward | Option 4 | Complete & in use |
| 19 | Central | Kiambu | Limuru | Limuru Digital Hub | – | Operational (Ajira, with centre manager) |
| 20 | Central | Kiambu | Juja | Juja NG-CDF Office Social Hall | Option 4 | Complete & operational |
| 21 | Central | Murang’a | Maragua | Sabasaba Education Zone ICT Hub | – | Complete (awaiting furniture) |
| 22 | Central | Murang’a | Maragua | Maragua National Library & ICT Hub | – | Complete (awaiting furniture) |
| 23 | Central | Kiambu | Gatundu S. | Gatundu Ajira Center | Option 4 | Complete & operational (old CIH) |
| 24 | Central | Nyandarua | Ndaragwa | Kiriita ICT Hub – Kirita Ward | Option 4 | Complete & operational |
| 25 | Central | Nyeri | Othaya | Mahiga ICT Hub – Mahiga Ward | Option 4 | Complete & operational |
| 26 | Central | Nyeri | Othaya | Iria-ini ICT Hub – Iria-ini Ward | Option 4 | Complete & operational |
| 27 | Central | Nyeri | Othaya | Witima ICT Hub – Karima Ward | Option 4 | Complete & operational |
| 28 | Central | Murang’a | Mathioya | Kamacharia ICT Hub – Kamacharia Ward | Option 4 | 90% complete (renovation, operational) |
| 29 | Central | Murang’a | Mathioya | Gitugi ICT Hub – Gitugi Ward | Option 4 | 90% complete (renovation, operational) |
| 30 | Central | Murang’a | Mathioya | Kiriaini ICT Hub – Kiru Ward | Option 4 | 90% complete (renovation, operational) |
| 31 | Central | Kiambu | Kiambaa | Karuri Digital Hub – Karuri Ward | Option 4 | 100% complete (needs furniture & computers) |
| 32 | Central | Nyandarua | Ol Kalou | Passenga CIH – Rurii Ward | Option 4 | Complete (needs furniture) |
| 33 | Central | Nyandarua | Ol Kalou | Wiyumiririe CIH – Kanjuiri Ward | Option 4 | Complete (needs furniture) |
| 34 | Central | Nyandarua | Ol Kalou | Olkalou NG-CDF Office Digital Hub | – | Complete & operational |

NORTH EASTERN REGION

| No. | Region | County | Constituency | Ward / Location | Model | Status / Completion |
| --- | --- | --- | --- | --- | --- | --- |
| 35 | North Eastern | Wajir | Wajir North | Buna ICT Hub – Buna/Batalu Ward | Option 4 (Renovation) | Construction 100% complete; awaiting equipping |
| 36 | North Eastern | Wajir | Tarbaj | Tarbaj Technical Institute – Tarbaj Ward | Basic | Construction complete (Aug 2025); awaiting computers & internet |

COAST REGION

| No. | Region | County | Constituency | Ward / Location | Model | Status / Completion |
| --- | --- | --- | --- | --- | --- | --- |
| 37 | Coast | Mombasa | Likoni | Likoni NG-CDF Digital Hub – Timbwani Ward | Option 4 | Complete & in use; requires full-time internet |
| 38 | Coast | Mombasa | Mvita | Mvita NG-CDF Office Digital Hub – Tudor Ward | Option 4 | Complete & in use; needs internet & more computers |
| 39 | Coast | Kwale | Matuga | Matuga Constituency ICT Hub – Tsimba/Golini Ward | Option 4 | Complete & in use; lacks internet connectivity |
| 40 | Coast | Kilifi | Kilifi North | Sokoni Digital Hub | Option 4 | Complete & operational; 40 desktops/workstations, Starlink internet, no NOFBI |
| 41 | Coast | Kilifi | Kilifi North | Watamu Digital Hub | Option 4 | Complete & operational; 30 desktops/workstations, Starlink internet, no NOFBI |
| 42 | Coast | Kilifi | Kilifi North | Matsangoni Digital Hub | Option 4 | Complete & operational; 31 desktops/35 workstations, Starlink internet, no NOFBI |
| 43 | Coast | Tana R. | Galole | Chewani Ajira Youth Empowerment Center – Chewani Ward | Renovation | Construction complete; awaiting computers from Konza (Kshs. 458,000 allocated for recurrent) |
| 44 | Coast | Lamu | Lamu East | Faza TVC Constituency Innovation Hub – Faza Ward | Option 4 | Complete & operational; desks & desktops in use but lacks internet & MoICT staff |
| 45 | Coast | Taita Taveta | Wundanyi | Wundanyi ACC Administration Complex Digital Hub | Standard | Hall construction complete; awaiting partitioning, equipment & furniture |

NORTH RIFT REGION

| No. | Region | County | Constituency | Ward / Location | Model | Status / Completion |
| --- | --- | --- | --- | --- | --- | --- |
| 46 | North Rift | Uasin Gishu | Ainabkoi | Illula ICT Hub | Option 4 | Complete; awaiting handover & MoICT to install internet + deploy centre manager |
| 47 | North Rift | Baringo | Baringo North | Simo – Kipsaraman | – | Complete & operational |
| 48 | North Rift | Baringo | Baringo North | Kabartonjo | – | Complete & operational |
| 49 | North Rift | Baringo | Baringo North | Bartolimo Primary School (CSR-funded) | – | Complete |
| 50 | North Rift | Turkana | Turkana West | Kakuma ICT Hub | Option 4 | Complete (Lokichogio & Kakuma hubs) |
| 51 | North Rift | Turkana | Turkana West | Lokichoggio ICT Hub | Option 4 | Complete |

WESTERN REGION

| No. | Region | County | Constituency | Ward / Location | Model | Status / Completion |
| --- | --- | --- | --- | --- | --- | --- |
| 52 | Western | Bungoma | Webuye East | Webuye East NG-CDF Office ICT Centre – Mihuu Ward | To be upgraded to CoE | Complete & in use (Ajira jitume operational, centre manager + 2 support deployed, NOFBI connected; no desktops from Konza; FY 2024/25 funds not yet utilized, procurement on hold pending e-GP rollout) |
| 53 | Western | Bungoma | Webuye West | Webuye West ICT Hub – Bokoli Ward | Existing CIH | Complete & in use; funds meant to purchase computers |
| 54 | Western | Kakamega | Matungu | Mayoni ICT Hub – Mayoni Ward | Option 4 | Complete & operational; connected to NOFBI (slow), 1 centre manager deployed |
| 55 | Western | Kakamega | Matungu | Koyonzo ICT Hub – Koyonzo Ward | Option 4 | Complete; not in use due to security; devices moved to Mayoni; no NOFBI |
| 56 | Western | Kakamega | Mumias West | Mumias West TVET – Musanda Ward | Option 4 | Complete & in use; not connected to NOFBI |
| 57 | Western | Kakamega | Mumias East | Mumias East NG-CDF ICT Hub – East Wanga Ward | Option 4 | Complete; not in use; not connected to NOFBI; awaiting launch (29 Sept 2025) |
| 58 | Western | Kakamega | Khwisero | Khwisero ICT Hub – Kisa North Ward | Option 4 (existing CIH) | Complete & operational; NOFB |

NYANZA REGION

| No. | Region | County | Constituency | Ward / Location | Model | Status / Completion |
| --- | --- | --- | --- | --- | --- | --- |
| 59 | Nyanza | Siaya | Alego Usonga | Karemo DCC Digital Hub – South East Alego Ward | Standard | Complete; awaiting furniture |
| 60 | Nyanza | Siaya | Gem | Mutumbu ICT Hub – North Gem Ward | Basic | Complete & operational |
| 61 | Nyanza | Siaya | Gem | Ulumbi Digital Hub – Yala Township Ward | Option 4 (Renovation) | Complete; awaiting furnishing |
| 62 | Nyanza | Siaya | Usigu | Usigu DCC Digital Hub – East Yimbo Ward | Option 4 (Renovation) | Complete |
| 63 | Nyanza | Kisumu | Nyando | Ahero Multipurpose CIH – Ahero Ward | Option 4 (Renovation) | Operational |
| 64 | Nyanza | Homa Bay | Kasipul | Oyugis Town ICT Hub – South Kasipul Ward | Basic | Operational (existing CIH) |
| 65 | Nyanza | Homa Bay | Kasipul | East Kamagak ICT Hub – East Kamagak Ward | Basic | Operational (existing CIH) |
| 66 | Nyanza | Homa Bay | Kasipul | Kachien South ICT Hub – Central Kasipul Ward | Basic | Operational (existing CIH) |
| 67 | Nyanza | Homa Bay | Kabondo Kasipul | Kasewe ICT Hub – Kabondo West Ward | Basic | Operational (existing CIH) |
| 68 | Nyanza | Homa Bay | Ndhiwa | Ratanga ICT Hub – Kwabwai Ward | Basic | Operational (existing CIH) |
| 69 | Nyanza | Homa Bay | Ndhiwa | Ndhiwa ICT Hub – Kanyamwa Kosewe Ward | Basic | Operational (existing CIH) |
| 70 | Nyanza | Homa Bay | Ndhiwa | Kobodo ICT Hub – Kanyamwa Kologi Ward | Basic | Operational (existing CIH) |
| 71 | Nyanza | Migori | Rongo | South Kamagambo Digital Hub – South Kamagambo Ward | Basic | Operational (existing CIH) |
| 72 | Nyanza | Migori | Rongo | Central Kamagambo Digital Hub – Central Kamagambo Ward | Basic | Operational (existing CIH) |
| 73 | Nyanza | Migori | Rongo | East Kamagambo Digital Hub – East Kamagambo Ward | Basic | Operational (existing CIH) |
| 74 | Nyanza | Migori | Rongo | North Kamagambo Digital Hub – North Kamagambo Ward | Basic | Operational (existing CIH) |
| 75 | Nyanza | Migori | Suna East | Kakrao TTI Digital Hub – Kakrao Ward | Basic | Operational |
| 76 | Nyanza | Migori | Kuria West | Nyamaharaga ACC Digital Hub – Isibania Ward | Basic | Complete; requires furniture, LAN & MoICT internet |
| 77 | Nyanza | Nyamira | Kitutu Masaba | Kitutu Masaba NG-CDF Office Digital Hub – Manga Ward | Option 4 (Renovation) | Complete |
| 78 | Nyanza | Nyamira | North Mugirango | Magwagwa Divisional Office Digital Hub – Magwagwa Ward | Standard | Complete |
| 79 | Nyanza | Nyamira | Borabu | Nyansiongo Digital Hub – Nyansiongo Ward | Option 4 (Renovation) | Complete |

SOUTH RIFT REGION

| No. | Region | County | Constituency | Ward / Location | Model | Status / Completion |
| --- | --- | --- | --- | --- | --- | --- |
| 80 | South Rift | Laikipia | Laikipia East | Laikipia East NG-CDF ICT Digital Hub – (Ward not specified) | Option 4 | Complete; requested Ministry for computers |
| 81 | South Rift | Kericho | Bureti | Kaminjeiwet ICT Centre – Chemosot Ward | Option 4 | Complete but not in use; awaiting computers from MoICT&DE |
| 82 | South Rift | Kericho | Bureti | Kibugat ICT Centre – Tebesonik Ward | Option 4 | Complete but not in use; awaiting computers from MoICT&DE |
| 83 | South Rift | Bomet | Sotik | Kamureito Digital Hub – Kipsonoi Ward | Option 4 (Renovation) | Complete & operational; needs expansion through renovation |
| 84 | South Rift | Kajiado | Kajiado North | Nkaimurunya ICT Hub – Nkaimurunya Ward | Basic | Complete; furniture tendering ongoing |
| 85 | South Rift | Kajiado | Kajiado North | Embulbul ICT Hub | Option 4 | Complete & operational; cabling materials on site, awaiting MoICT&DE connection |
| 86 | South Rift | Kajiado | Kajiado North | Ngong ICT Hub | Option 4 | Complete & operational; connected to NOFBI; centre manager deployed |
| 87 | South Rift | Kajiado | Kajiado North | Ongata Rongai ICT Hub | Option 4 | Complete & operational; awaiting MoICT&DE internet & centre manager |
| 88 | South Rift | Nakuru | Nakuru Town East | NG-CDF Office Digital Hub – Nakuru East Ward | Option 4 | Complete; 52 desktops installed; no NOFBI; no centre manager |
| 89 | South Rift | Nakuru | Kuresoi South | Keringet ICT Hub | Option 4 | Complete & operational; funded for equipping existing CIHs |
| 90 | South Rift | Nakuru | Kuresoi South | Tinet ICT Hub | Option 4 | Complete & operational; funded for equipping existing CIHs |
| 91 | South Rift | Nakuru | Kuresoi South | Amalo ICT Hub | Option 4 | Complete & operational; funded for equipping existing CIHs |
| 92 | South Rift | Nakuru | Kuresoi South | Kiptagich ICT Hub | Option 4 | Complete & operational; funded for equipping existing CIHs |
| 93 | South Rift | Nakuru | Molo | Sachangwan Digital Hub – Chief’s Office, Molo Ward | Basic | Complete |
| 94 | South Rift | Nakuru | Gilgil | Gilgil NG-CDF Office Digital Hub | Basic | Complete |

Bottom of Form